## Issues
Status: | C | Closed
| CM | Closed Merged into another issue No.
| HT | Hardware Test, means issue should be retested on real Apple HW to ensure it is not an AppleWin related problem (timing).
| V | Verified, means issue was retested and still exists. Build Col will show orig build issue appeared and last tested build.
Status | Issue No. | Command | Build | Behavior | Comment | Fixed in…
C | 100 | SLEEP | 1004 | Always gives Syntax Error.
C | 101 | ARP | 1004 | Main memory drops after running command.
CM | 102 | CP | 1004 | Fails with lowercase filenames. Works when you supply uppercase names. When you specify a file name that already exists, it prompts you to overwrite as it should.
C | 103 | DNSINFO | 1004 | With network unloaded, running command gives No Device Found, then locks system. | Same correction applied to ARP. Fixed. | 1018
C | 104 | EDIT | 1004 | I was getting ERROR 40 and other strange behavior. Do edit with no filename (or with one) and then type stuff and then Ctrl-S and first thing press Escape and type stuff. I can also consistently get EDIT to lock up when typing text after using the delete/bs keys. | Verified in latest. Boot, -run, at prompt EDIT A. Then type some stuff, then ctrl-S PRESS ESCAPE and then type aaa and return. Error 40 | 1034
HT | 105 | IPCONFIG | 1004 | Seems to work, though it shows for Link Status: Media Disconnected when that clearly is not the case. | Which NIC/Driver ? -RG This is on AppleWin using NET script. I need to test this on a real Apple, it may be the Eth driver in AppleWin is reporting it wrong to you. -PK
CM | 106 | L/LS | 1004 | If you pass command a lowercase filename/wildcard, it does not return any results, but uppercase FNs work fine.
C | 107 | MD | 1004 | Works, but I could not figure out how to remove a directory I created with this command.
C | 108 | MD5 | 1004 | Does not generate the right hashes. |  | 1019
C | 109 | MORE | 1004 | Works, no problem with lowercase file names. Line numbering does not work. Piping to MORE (L ¦ MORE) does not work at this time. | -N implemented (Pipe is SHELL related) | 1022
CM | 110 | MV | 1004 | Has lower case issue. When it does rename files it ends saying that 0 Filecat(s) were Moved. Even though it did move files.
C | 111 | PING | 1004 | Ctrl-C out of ping and lead to BADMEM errors. | Was GH #40, closed there too. | 1039
V | 112 | PS | 1004 | PS will take an argument and just ignore it (“PS 44” or “PS A”) should it instead give syntax error and display usage message.
CM | 113 | RM | 1004 | Works. Doesn’t work with lowercase filenames. RM with wildcards works and shows you the names of the files it removes and correctly displays the total number of files removed.
C | 114 | TELNET | 1004 | Telnet (the network) does not resolved host names unless they are defined in the HOSTS file. The telnet session seemed to work fine, I saw no dropped characters or anything. When telling the remote host to terminate the call though, TELNET just sat there. Ctrl-C did exit. NETSTAT says host is FIN-WAIT-1. This is A80s BBS not a linux box. After doing that NETSTAT then an L etc and then cat etc/hosts system locked in the middle of typing the next command. TELNET to a host name listed in etc/hosts does resolve to the right IP address and gives you “Connected” but then it hangs. Ctrl-C and then NETSTAT gives you FIN-WAIT-1 to a linux host. 4K of memory is lost in this process (mem after TELNET ctrl-C).
C | 115 | KERNEL | 1004 | CloseMerging all upper/lower case file name issues from above into this one master issue. A separate note should be written up on this topic specifying the desired behavior for all commands and APIs. | Tested with multiple commands. No issues found 1047.
V | 116 | TELNET | 1016 | All Telnet sessions when terminated from the host end with a Socket Error : $27
C | 117 | DNSINFO | 1016 | DNSINFO host Ipaddr does not add the passed entry to the local dns table. | Type DNSINFO ME 1.1.1.1 and after do another DNSINFO and see that ME was not added | 1034
C | 118 | SLEEP | 1016 | At shell prompt does nothing. In script it pauses and waits for a keypress regardless of parameter passed. |  | 1020
V | 119 | EDIT | 1027 | Edit cannot keep up with a moderate amount of typing. It starts dropping characters. | I can still get it to drop chars if I type fast enough (I can type fast, a hunt and pecker will not see this issue).
C | 120 | KERNEL | 1016 | Something is causing the system to lock up at the shell prompt right in the middle of typing a new command (you go to type CAT and after typing C the system hangs). I am not sure what command(s) is leading to this. | I have not seen this again in the latest builds and cannot repeat so closing issue. PK | 1026
C | 121 | SHELL | 1016 | If you do a PAUSE or SLEEP command at the shell prompt, the prompt starts to act weird. After each command (LS or CAT) the command does what you want (display a dir) but then sits there blinking at you until you press return and then the prompt appears. It keeps doing this until you reboot. | quick fix for PAUSE:limited to CR -RG Sleep is fixed, Pause working for return only. Will Close this issue but open one for PAUSE to accept keypress. | 1020
V | 122 | SHELL | 1017 | $# reports 2 In IFTEST, it should be 0 as no args are passed to IFTEST. IFTEST arg1 arg2 would report 2. That is why the shell and command file have special vars and are not "args" and counted in arg count. | $# now reports 1 high. It reports 1 when no args are passed, and 12 when I pass 11. This is in 1047
V | 123 | MORE | 1027 | When you CAT IFTEST you see the whole file, but if you MORE IFTEST, the screen clears and then the file displays. I believe it is processing the \f on the first line of the file. This may be good for things like MAN pages that are designed to be formatted, but not desirable for displaying code like IFTEST. I suggest a option be added to MORE (-S process screen codes) that will do the clears and other VT100 codes, but that the default behavior is to NOT process these codes and behave more like CAT.
V | 124 | MORE | 1027 | After MORE displays a page of text and pauses waiting for input, SPACE should display another page (which it does), RETURN should display one more line. Q (single letter q) should exit more immediately and return to command line.
C | 125 | CAT badfile | 1027 | CAT of a file that does not exists does not return an error, should return "cat: badifle: No such file". | Related to issue 127.
C | 126 | SHELL exit | 1027 | Exiting shell (Ctrl-D) then relog in puts you in a nomans land for CD/PWD and then gives FreeMem error. | Closed CD/PWD issue fixed, but other/more problems see #133.
C | 127 | SHELL Return Codes | 1034 | $? Does not report return codes properly or return codes are not being set by commands/scripts. There should also be an explicit RETURN statement for scripts so you can return your own codes from one script to another and check them. | Moved from S0022.
HT | 128 | ThunderClock |  | Need to verify that A2OSX works on real Apple with Thunderclock installed. Test Slots 1 2 and 3.
V | 129 | PING | 1034 | Ctrl-C now gives FreeMem:52=Bad hMem (or 53). I was able to reproduce reliably, boot, -RUN, login, NET then PING 10.0.0.67 and Ctrl-C after 10 or so pings. | missing stz hFrameIn in LIBTCPIP.S.ICMP Confirmed still in 1047 | 1039
V | 130 | Startup Bypass | 1034 | From GH #35, implement Ctrl-D bypass of startup file. Tested, confirm bypass works, but when you get the prompt, if you press Ctrl-D again it locks up the system. This becomes a problem because people might hit ctrl-d multiple times at start to bypass and the extra one then locks you up. | GH #35
C | 131 | TELNET | 1037 | On a Linux host, if you are doing something that productes a lot of output (ls -l /usr/bin or ps -ef) there are times of noticable pauses and they grow longer and longer. And in Linux if you want to abort the command and get back to prompt its Ctrl-C, which aborts TELNET (its handled locally rather than passed to session). For Telnet you should pass Ctrl-C then have another abort key or sequence (maybe Escape Ctrl-C). | Switched to Ctrl-T | 1050
C | 132 | L | 1037 | Boot, you are in A2/ROOT. Type L, gives right listing. Type CD .. You are moved to top of VOL. Type L again and you get the listing for ROOT. Ls dispplays the right listing. Note too, the script file for L seems wrong, It should start with $1? And for whats its worth, there is no L command so this should probably jsut go away. |  | 1047
| 133 | EXIT | 1047 | 1) Boot, then EXIT then re-login (return/return) after 2nd return you get a "FreeMem:hMem already freed,BIN=/A2OSX.BUILD/SBIN/SHELL" message. Then prompt as expected. 2) Boot, then NET, then EXIT, then re-login try LS, CRASH to monitor or worse.
| 134 | PAUSE | 1047 | PAUSE should accept any keystroke to continue not just return. | Planned 0.93 or after.
CM | 135 | PING | 1047 | When you cancel a ping with Ctrl-C you get a [$03]:Unknown Error. | Merged into 138, its happens on all commands.
| 136 | PING | 1047 | When you ping a host, sometimes it starts listing returns, other times it just sits there for 5 secs before giving timeouts and then sometimes you get 2-4 returns and then the time outs. This is to know good hosts. | Beware of bad VBL emulation in Applewin should be flagged HT
HT | 137 | NSCUTIL | 1047 | Always returns syntax error. Tried NSCUTIL 12/21/21 17:12:35 | side note : Applewin does not allow Writing to NSC should be flagged HT | 1050
C | 138 | KERNEL | 1047 | Control-C out of many programs (telnet, ping, memdump) end with [$03]:Unknown Error. | Remapped $03 to "User Interrupt" Error message | 1050
| 139 | LS -R /VOLNAME | 1047 | If you do an LS -R /VOLname like "LS -R /A2OSX.BUILD" it will list only PART of the top dir and then give you a volume error $45. | L -R /VOLNAME/ works….miss adding / for proper PATH recursion. CP,MV,RM should also be impacted | 1050
| 140 | LS | 1047 | L on etc, bin, anydir responds quickly. L to / there is a little pause (to be expected) before listing volumes. L /PKA2OSX (my virt drive) respomnds little delay but L /A2OSX.BUILD there is a long pause (+3sec) and then listing.
| 141 | REN | 1047 | REN /vol /newvol works. But REN file newfile returns [$40]:Invalid path. REN dir newdir also error 40. if you REN /vol/file /vol/newfile it works. | REN is a simple binting to ProDOS API: syntax is : REN oldpath newpath if you want REN oldpath newNAME, it is an enhencement | Change name to RV or MV
C | 142 | ECHO | 1047 | echo \e does not seem to do anything. This is inverse yes? I tried in script ECHO "abc \e def \e hello" and no inverse. Tested \b \f \n \% \\ all ok. | \e is ESC INV = \e[7m NORM = \e[0m to do what you want you need: ECHO "abc \e[7m def \e[0m hello" | no fix needed
C | 143 | SHELL $PWD | 1047 | At command line PWD shows right value, but in script it shows $HOME though I am in a different dir. If you change HOME at cmdline and then run script $PWD in script displays new HOME value. MORE on this. My current dir is /PKA2OSX/TESTS, I do LS no prob. I do L and I get listing for /A2OSX.BUILD/ROOT. I manually change HOME to PK/TESTS and do L again and I get the right dir. Somehow L is looking at the same mem address the $PWD is to do the listing or something. | $PWD always reset to $HOME | 1050
| 144 | RPCDUMP | 1047 | Locks system regardless if NET loaded or not.
| 145 | SHELL script | 1047 | In a script file I have the line "CAT IFTEST" that when the script is run returns an Error 46:File Not Found and the debug ----^ ends 2 spaces after the end of the filename on the line. If I put CAT /PKA2OSX/TESTS/IFTEST then it works. I think this is related to 141.
V | 146 | DNSINFO | 1047 | If you add a host with DNSINFO myhost 10.0.0.88 and then add the same host again (repear command) the DNS table appears to get corrupted (pasted image in Slack) | DNSINFO did not check TCPIP status before managing DNS cache. Always resetting cache before displaying/updating | In 1050, half fixed. If you DNSINFO host ip twice in row from command line no more problem. but if DNSINFO host ip is in script, 2nd time you run script machine LOCKS at that line in script, so calling from script is bad some how.
147
148
149

## Suggestions
Status | Suggestion No. | Command | Suggestion | Target | Comment | Build
| S0001 | LS | LS and L should have an option [-s] that sorts the output by filename. Potentially there should also be sort options for date [-d] and type (BIN,TXT,etc) [-t]. | 0.93
| S0002 |  | Should MEMDUMP.S and RPCDUMP.S be in BIN/DEV or do these belong on the SRC disc? | 0,92 | A2OSX.SRC is FULL - Will merge BUILD+SRC in a HD image (32mb) booting MASM3.SYSTEM - Rename BUILD -> BOOT800, booting A2osX - Create a script MAKEB800 to build BOOT800
| S0003 |  | NET (and whatever it loads) takes a lot of Main Memory (almost 15K). Is there a way to reduce this or get it shoved into Aux Memory as this will have a significant impact on the size of programs people can write. | 0.93 | Multi Protocol stack - Remove Config Code in LIBTCPIP - Merge Config Code+DHCPCLNT -> IPCONFIG (new switches : -d -s -r) - Rename TCPIPD -> NETD - Make LIBTCPIP,LIBETLK... to be bound to ETHx by NETD - Add etc/netd.conf for protocol binding
| S0004 | DATE | The DATE command should have options for returning the Day of Week (-w) as # (-W) as word, month (-m) as # (-M) as word, the day (-d) and the year (-y) 2 digit (-Y) 4 digit. | 0,93
| S0005 | WHO | Need a who command once we have logins going. | 0.93
C | S0006 | CLS | Need a clear screen command CLEAR or CLS.
| S0007 | V/H TAB | Need something along the lines of Basics VTAB HTAB so we can position the cursor before an Echo statement. This may also require a way to do Echo's that don’t have CR/LF.
| S0008 | ECHO | A way to echo special chars (VT100 stuff, MouseText Chars). Also echo should support standard special chars \n Newline \b backspace \t tab \0nnn ascii char nnn. | 0,92 | Some already impemented, see GH readme.md
| S0009 | WC | Word (-w), Line (-l) and Char (-c) count command.
| S0010 | CUT | We need a cut command which could be used to pull fields of data out of output or files (CUT file types out of L listings, or CUT user ID from passwd file). -d option to delimit by char (:). -f pulls fields by that delimiter.
| S0011 | GREP | Parse lines and filter by pattern.
| S0012 | EXPR | One option to adding a complete/extensive expression evaluator into the shell (making it bigger) is to move this to a separate command EXPR.
| S0013 | SHELL CASE | Case statement in shell.
| S0014 | FOR | FOR x in list, DO … DONE
| S0015 | WHILE / UNTIL | Add to the shell support for WHILE and UNTIL loop constructs. | 0,92
| S0016 | profile | Some of the things in STARTUP should problably be in an /etc/profile file (set PATH, TERM, PS1, etc.)
C | S0017 | $0-S9 vars; SHIFT | Does shell/script support the standard way of accessing arguments/parameters, $* for all, $1 first 1, SHIFT to eat $1 and move others left. $0 pgm name $# num args. |  | ARGTEST and SHIFTTEST created.
| S0018 | PRINTF | A command version of C func. Basically a very advanced version of Echo that allows formatting. By making it external, can save mem of code/data space. |  | CSH
| S0019 | ProDOS | The Version of ProDOS on BUILD (and I assume BOOT) is V2.0.3. The most current version is 2.4.2. We should update the version of ProDOS on our discs to match (largley to keep up with the date/clock corrections) and bug fixes. |  | GH #26
| S0020 | UNAME | Make a new Program called UNAME. By default it should return the HOSTNAME, System Type (//e, gs. Etc), OS Name, Version (0.92), boot device, etc. Their should also be options (-H hostname, -S systype, -V version, etc), for each data item so one can write programs that get just the bit they want (like current os version).
C | S0021 | VOL | There should be a VOL or VOLUME command that allows you to get or set the name of a VOLUME by device ID (S7D1). There should be a VOL - A option that lists all vols by device (like L /) but VOL command sould list drives with no VOL. This command would be the way to rename a volume. | 0.92 | REN works with file dir, and volume
C | S0022 | RETURN Code | It would be nice to implment $? (if I echo that I always get 0 so I think you are already planning this one). Allow a SCRIPT to set it (RETURN 1 or RETURN 10 or RETURN 0 etc). Also commands should set RETURN codes based on success. This code has to pass back between shells (can't be lost like ENV is). |  | Closed, moved to issue 127.
C | S0023 | STARTUP | I suggest renaming the A2OSX.STARTUP file to INIT and placing in the ETC directory. A2OSX.SYSTEM should look for it there. | 0,92 | GH #4 | 1039
| S0024 | MAN | Need a product specification for V1.0 and V2.0 of MAN system. |  | Assign to PK
| S0025 | Logo | We need an 80x40 pixel 16 color logo. BMP format, A2OSX has tool to convert to PIX. |  | my son did it ! Coming soon…
| S0026 | PIX | Need to document PIX format. Need to write PIX image viewer/editor/ |  | GUI…. Same for "FNT": A2osX bitmap font format
| S0027 | License | Need to pick a license type and put a license file on the disks. |  | Assign to PK
| S0028 | Shutdown | There should be a shutdown command that closes open sockets, open files, executes ETC/INIT0 script and then does standard ProDOS exit (loads bitsy.bye type thing). IS that what QUITCODE is? | 0,93 | SHELL will handle SYS files, calling API shutown with arg=.SYS file this will pass .SYS file to A2osX QC
| S0029 | DB Engine | PK to write spec sheet for a DB Engine or client/servier API for DB.
| S0030 | Screen Shots | PK to update Screen Shots on GitHub and in Readme. |  | PK
| S0031 | Recruitment | Contact blondie7575 from GH about joining project for adding WeeGUI
| S0032 | RD | Like there is MKDIR alias for MD, there should be an alias RMDIR for RD. BTW, why is MKDIR BIN? What extra is there as a bin rather then a script? Like L is to LS.
| S0033 | MD5 | MD5 should return its result in all lowercase (as do most other MD5 utils/sites).
| S0034 | DNSINFO | There should be a way to remove an entry to manually added.
| S0035 | COMP | A file comparison tool to see if too files are equal. In the short term I can write a script that uses MD5 to hash both files and if the hash is the same the files are the same.
| S0036 | PROFILE | Have login run /etc/profile at user login ($SHELL -N $ROOT/ETC/PROFILE)
| S0037 | USERADD | Should create an entry in etc/passwd with USER:PW:UID:GID:GECOS:HOME:SHELL
| S0038 | SHELL | When editing a previous command (hit up arrow) and you move left and change a letter or two and press return to execute command it clears the remainder of the line. Bash retains the whole line and executes edited command. |  | Future enhancement
| S0039 | Doc | Make a list of the VT100 codes you can use with echo and what they do. |  | PK
| S0040 | EDIT | Needs to be rewritten to use buffered IO and be preemptive compliant
| S0041 | Doc | We need a document that discusses the tools and processes one uses to work on the A2OSX project. Examples include the TortoiseSVN package to contribute, MarkDownPad to edit MD and other DOC files on github. Github tools and registration. How to edit, compile and run a program under A2OSX.
| S0042 | Doc | We need a document on how to install A2OSX on your existing ProDOS HD/CF Card.
| S0043 | Doc | Need to document setting up and using SSC. What is needed on both client and server computers, what VT100 software to use, etc. What is diff between SSC and SSCI?
| S0044 | Doc | Same with setting up and using TELNETD
| S0045 | Doc | Need to document as a way to stop error messages if they start scrolling on screen (like FreeMem). Can also be used during boot to see msgs at each stage.
| S0046 | Doc | Write one doc for all SHELL internals, redirection, etc. and need to talk about "." before script.
S0047
S0048

## Commands
This new sheet has multiple purposes. 1) It is to make sure that every command is being tracked and we have 1 complete list somewhere. 2) To track completion of commands (Col C, RG), that doc is written if appropriate (B, PK), a MAN page is written (E, PK), a test script is written for the command (F, PK) and that each command has imbeded help/usage (-h option) (Col G, RG).
Command | Comp. | Doc. | Manpage | Test | Help (-h) | Comment